## Project Information
I. Requirements
Công ty Hi-Tech là một công ty chuyên kinh doanh về các thiết bị điện tử và công nghệ thông tin trong nhiều năm nay và đã có một lượng khách hàng nhất định. Để mở rộng hoạt động kinh doanh của mình, công ty mong muốn xây dựng một hệ thống thương mại điện tử nhằm mở rộng phạm vi kinh doanh trên mạng Internet. Hệ thống mới phải đảm bảo cho khách hàng viếng thăm Website dễ dành lựa chọn các sản phẩm, các chính sách của công ty cũng như mua hàng. Việc thanh toán có thể được thực hiện qua mạng hoặc thanh toán trực tiếp. Khách hàng có thể nhận hàng tại cửa hàng hoặc công ty sẽ có dịch vụ chuyển hàng có phí cho khách hàng. Ngoài ra, hệ thống cũng cần có phân hệ để đảm bảo cho công ty quản lý các hoạt động kinh doanh như số lượng hàng có trong kho, quản lý đơn đặt hàng, tình trạng giao hàng v.v… Thông tin chi tiết các chức năng bạn có thể tham khảo thêm tại: http://www.bkc.vn/M/Home

## Team
TEAM DEVELOPMENT STRUCTURE
No. | Name | Account | Roles | DateStart | Date End
1 | Nguyễn Văn A | Anguyen | Product Owner | 2014-01-25
2 | Trần Thị B | Btran | ScrumMaster | 2014-01-25
3 | Huỳnh Thanh Cảnh | CanhHuynh | Team Lead | 2014-01-25
4 | Nguyễn Thịnh Can | CanNguyen | Dev | 2014-01-25
5 | Lê Văn Ái | AiLe | Dev | 2014-01-25
6 | Phùng Văn Tính | TinhPhung | Dev | 2014-01-25
7 | Lê Thị Lụa | LuaLe | Dev | 2014-01-25

## Product backlog
E-COMMERCE PROJECT - PRODUCT BACKLOG
Story ID | Story Name | Points
83
Actor: Guest
1 | View HomePage | 4
2 | View Product list | 4
3 | View Product details | 2
4 | View Product Compare | 2
5 | Manage Shopping Cart (Add, Increase, Decrease, Remove) | 4
6 | Registration | 4
7 | Chat with Sale | 4
Actor: Customer
8 | Login | 2
9 | Make Orders | 2
10 | Order Management (View, Cancel request) | 6
11 | View Shipping Progress | 2
12 | Online Payment | 4
13 | Logout | 1
Actor: Order Processing
14 | View New Order | 2
15 | Order Management (View, Short, Update) | 4
16 | Shipping Management | 6
17 | Offline Payment | 2
18 | Payment Mornitoring | 2
Actor: Sale Manager
19 | Product Management | 6
20 | Store Management | 4
21 | Inventory Management | 6
22 | Price Management | 4
23 | Promotion Management | 4
Actor: Administration
24 | User Management | 6

## Sprint backlog
E-COMMERCE PROJECT - SPRINT BACKLOG
Story ID | Story Name | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
16
Sprint 1
1 | View HomePage | 4 | CanNguyen | 2014-01-27 | 2014-01-28
2 | View Product list | 4 | CanhHuynh | 2014-01-27 | 2014-01-28
3 | View Product details | 2 | CanhHuynh | 2014-01-29 | 2014-01-29
4 | View Product Compare | 2 | CanNguyen | 2014-01-29 | 2014-01-29
5 | Manage Shopping Cart (Add, Increase, Decrease, Remove) | 4 | AiLe | 2014-01-27 | 2014-01-28
6 | Registration | 4 | TinhPhung | 2014-01-27 | 2014-01-28
7 | Chat with Sale | 4 | LuaLe | 2014-01-27 | 2014-01-28